

***Progress Report for Tangaroa Ara Rau***

***Relationships with Māori***

*As at 25 July 2019*

**WSNZ lead Neil McInnes/Sheridan Bruce**

**TAR partners Zack Makaore, Pereika Makiha, Chanel Phillips**

**Achievements**

* **WSNZ’s Kaihautu Māori recruited and is providing te reo and tikanga training, and support on Māori engagement to WSNZ staff**
* **Pre-production of documentary series on Māori water safety underway and excerpts to be used in upcoming Drowning Prevention Summit**
* **As part of finalising Bay of Plenty Water Safety Strategy, WSNZ engaged with several iwi and Māori organisations (including BoPRC Komiti Māori)**
* **Participation of Ngati Porou SLSC in expansion of WSFL programme agreed in principle**
* **Consultation with Māori on Waikato water safety strategy scoped**

**Current challenges or issues**

* Greater understanding of current iwi interest and activity in drowning prevention needed
* Funding from Te Māngai Pāho for completion of documentary series yet to be confirmed.
* More work needed to identify where Māori communications professionals are best placed to support WSNZ and where developing internal capability for engaging with Māori is best
* Objectives for, and potential partners to help with, Māori water safety workforce development to be identified

**Next steps**

* Confirm funding from Te Māngai Pāho for completion of documentary series
* WSNZ’s engagement with iwi/ Māori to continue, especially in regions with water safety strategies
* Framework for Māori water safety workforce development to be developed

**Overall rating**

|  |  |
| --- | --- |
|  | * **WSNZ’s Kaihautu Māori is providing support on Māori engagement**
* Te Māngai Pāho funding for completion of documentary series to be confirmed
* Framework for Māori water safety workforce development to be developed
 |

***Key***

On

Significant Risk;

intervention required

Underway – some challenges

Being managed

On track

No issues

On track and or in pipeline

No issues or risk