

***Progress Report for Tangaroa Ara Rau***

***Kia Maanu, Kia Ora***

*As at 25 July 2019*

**WSNZ lead Sheridan Bruce**

**TAR partners Mark Haimona, Jordan Waiti, Ashlea Williams**

**Achievements**

* Māori outcomes included in funding priorities section for 2019/20 WSNZ funding prospectus
* **ACC funding of $1.0 million over two years for WSNZ for kaupapa Māori drowning prevention initiatives confirmed**
* **Overall funding allocations for kaupapa Māori drowning prevention initiatives agreed with ACC and engagement started with those providers not part of WSNZ 2019/20 funding round**

**Current challenges or issues**

* WSNZ 2019/20 funding round massively oversubscribed and NZLGB funding reduced by $160,000 – therefore not all **Māori** funding applications were successful
* ACC funding comes with requirements to develop evaluation framework in first year, reducing initiative funding available for allocation
* Aligning priorities for regional water safety strategies with **Kia Maanu, Kia Ora** outcomes to be identified

**Next steps**

* **Kia Maanu, Kia Ora funding recipients to be advised first week of August**
* Finalising ACC contract and meeting with ACC **Māori and Cultural Capability Team**
* Scoping how the **Kia Maanu, Kia Ora brand will operate as a certifying mark**

**Overall rating**

|  |  |
| --- | --- |
|  | * **ACC funding for WSNZ for kaupapa Māori initiatives confirmed**
* WSNZ to finalise ACC contract and meet with ACC **Māori and Cultural Capability Team**
* **KMKO funding recipients to be advised first week of August**
 |

***Key***

On

Significant Risk;

intervention required

Underway – some challenges

Being managed

On track

No issues

On track and or in pipeline

No issues or risk